## Landfill Design and MgMt
Green Island landfill - Section 92 Responses Tranche 4
Landfill Design and Management
Contacts - NICK ELDRED, P LANDMARK
Technical reports - LANDFILL DESIGN REPORT, LDMP
Section 92 request
Landfill Design | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
7. It is noted that the design report refers to a gradient of 4.5% for the cap. Where is the cap a 4.5% grade. Is that the average grade, or specific parts of the landfill? | Desktop | This is mentioned in one location in the report (4.2.2). It is a hangover from an earlier assessment and oversimplifies the design. This has been edited and revised and the report re-issued 29 September. | Yes - see updated Design Report issued 29 September.
12. On drawing C304, is the label for “Intermediate cover” located on the correct layer? | Desktop | This label has been removed and drawing updated. | Yes - see updated Design Report issued 29 September.
15. Please confirm if there is a maximum thickness value for the layers mentioned in questions 12-14 to ensure compaction is achieved throughout the relevant cap layer. | Desktop | Intermediate capping will be compacted in one layer to achieve a 300mm thickness as intermediate capping is to be placed directly on the waste and compaction in multiple thin layers risks incorporating waste into the compacted layers. All other materials should be compacted in layers of no more than 200mm compacted thickness | Yes - see updated Design Report issued 29 September.
16. Section 6.2 states cover graded to the stormwater system to allow runoff of uncontaminated water and reduction in leachate volumes. Confirm which soil layer this is referring to, noting that section 4.4.2.2 of design report and section 3.5.2.3 of the Landfill Design Management Plan (LDMP) indicate that water coming into contact with intermediate cover is leachate, and section 3.5.2.3 of LDMP implies that only water off final cap can be treated as clean. |  | The LDMP and Design Report have been updated to address this issue. Note: Section 6.2 is referring to the final cover. Note the more fullsome description of how intermediate cover runoff will be managed in the relevant sections of the LDMP and Design Report. | Yes - see updated Design Report issued 29 September.
17. Please provide clarity on the timing of placing intermediate cover, and the timing of topsoiling intermediate cover, noting that; • Section 4.3.4 of LDMP states that intermediate cover will be topsoiled at earliest opportunity; • Section 4.11.1.6 says if waste not expected to be placed for 3 months then another layer of daily cover will be applied; • section 4.11.2 says intermediate cover will be placed on areas not being worked for 6 months; and • section 4.11.2 says surfaces exposed for more than 3 months will be topsoiled and grassed. | Desktop | The LDMP and Design Report have been updated to clarify the timing of intermediate cover and how vegetation will be managed. In summary: intermediate cover is applied to areas expected to not receive further waste for 3 months; vegetation growth on intermediate cover is encouraged. | Yes - see updated Design Report issued 29 September.
18. Section 4.10.1 of LDMP refers to primary cover. Please clarify what “primary cover” is. | Desktop | The LDMP has been updated. Ths has been chanegd to "daily" cover. | Yes - see updated Design Report issued 29 September.
19. Section 4.11.3.2 of LDMP refers to cap being subject of “approval by Engineer”. And section 4.11.3.7 rules out permeability testing on the cap. a) Confirm who is the engineer being referred to here - is it the design engineer? b) Confirm if the cap will be subject to detailed design which would detail CQA testing. | Desktop | The design of the cap will be consistent with the “GHD 2021 Green Island Landfill Capping – Design Report”. The LDMP has been updated to reflect this requirement. | Yes - see updated Design Report issued 29 September.
20. Section 4.11.3.8 states that services not installed closer than 0.3 m above the base of the final cover clay layer. a) Please confirm if 0.3m above the base of the clay cover layer will be in the middle of the clay cover layer? b) Does the above mean the pipes will be in the compacted clay layer? c) Could this inhibit the performance of the capping system? Will the pipes be able to withstand the compactive force from cap construction? | Desktop | LDMP has been updated to addres this question - see Section 4.11.3.8. | Yes - see updated Design Report issued 29 September.

## Leachate and Groundwater
Green Island landfill - Section 92 Responses Tranche 4
Leachate and Groundwater
Section 92 request
Leachate and Groundwater | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
22.Section 3.3 of LDMP refers to maintaining a groundwater divide by engineered groundwater control adjacent to landfill footprint. Please confirm if this is the leachate collection trench, or a separate system? If it is separate, please explain what this system is and provide plans showing this. | Desktop | The LDMP has been updated to clarify this issue. In summary, the LDMP is refering to the Leachate Collection System. | Yes - see updated LDMP issued 29 September.
26. The leachate collection system (LCS) is shown on a number of drawings and with other information about the site shown, it makes it difficult to fully understand the existing and proposed LCS layout. Please provide drawings that clearly show the leachate collection system (both existing and proposed) without other non-leachate collection system details (e.g. contours) for a clearer understanding. | Desktop | An additional drawing has been included with the updated design report to clarify this issue (C205). | Yes - see updated LDMP issued 29 September.
27.It is noted that the drawings and design report include a variety of terms that seem to be related to the LCS. It appears that some terms may be interchangeable which is confusing for the reader. Please provide updated drawings which use consistent terminology across the drawings and the design report. Some examples of the terms on the drawings legends are; • Dwg G101: o Existing leachate drain; and o Existing leachate drain in waste; • G102: o Existing leachate drain; o Existing leachate drain in waste; o Pipe flow; o Interception trench; o Southern interception trench; and o Extent of new leachate collection system. • C204: o Extent of leachate collection system; o Primary leachate collection drain; o Leachate drainage pipe; o Existing leachate drain in waste; o Existing leachate drain perimeter; and o Interception trench (new). • C304: o Section detail of primary leachate drain; o Interception trench detail; o Primary leachate drain detail; o Design report terms; o Leachate ByPass drain; and o Open swale drain. | Desktop | The drawings have been reviewed and any inconsistency in terminology addressed on the drawings. The design report has also been updated for consistent terminology. See attached. | Yes - see updated LDMP issued 29 September.
30. Furthermore section 6.1 refers to infrastructure for air operated leachate pumps in gas wells. Please provide full details of what infrastructure is proposed and where, and what the intent of the infrastructure will be e.g. to reduce leachate levels to specific target levels. | Desktop | The approach is described in the response to Q23 and the Design Report. The geotech section of the design report and proposed discharge of waste to land condition 9 describes the target management levels for leachate within the landfill waste. This requires DCC to implement all practicable measures to maintain these levels, which may also may include installation of air lift pumps within the landfill gas wells which will be used to abstract leachate from the waste mass. Note the approach and design of these instruments will be included in the LDMP when consents are granted and are currenly included in the list in Appendix 18 - LDMP Summary of Recommended Changes. | Yes
32. Section 4.4.1 provides definitions of leachate. What is the definition of stormwater that runs off the intermediate cap? Is that leachate, and if so, should it be included in this definition also? | Desktop | In almost all circumstances stormwater that runs of the immediate cover is defined as "leachate". However, by exception, runoff from some areas of intermediatate cover where there is no risk of leachate contamination has been treated as stormwater. | Yes

## Landfill Gas and Design Life
Green Island landfill - Section 92 Responses Tranche 4
Landfill Gas and Design Life
Section 92 request
Landfill Gas and Design Life | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
35. Drawing C501 appears to show some Landfill gas wells (LFG) wells on the 1:3 sloped area of the cap in the south west area of the landfill (e.g. Wells GW90, GW91 etc..). | Further assessment | This has been addressed in the updated T+T LFG Management letter dated 21/09/2023 | Yes - see T+T letter 21/09
36. Design report states that LFG collection averages 251 m3 /hr, compared to estimated generation rates of over 800 m3 /hr in 2021 and 2022, and estimated LFG collection rates of 648 m3 /hr and 666 m3 /hr in 2021 and 2022 respectively. | Further assessment | This has been incorprated into the revised T+T LFG Masterplan. This is a September 2023 update of the Masterplan submitted with the GI consent application documents. | Yes - see T+T Masterplan update 30/09
37. The capacity of the LFG treatment system seems to be 800 m3 /hr if both the engine and flare are operating at full capacity. This is below the peak LFG generation rate estimated via LFG modelling, although it is above the maximum modelled capture rate of 745 m3 /hr (section 3.3 of LFG Masterplan in Appendix C of design report). If LFG collection efficiency increases, is there potential for a short fall in LFG treatment capacity noting that the WWTP contributes biogas to the engine, and the engine seems to have been down for significant periods in the previous financial year (approx. 1 month in March April 2022; and other periods of a week or more) meaning only the candlestick flare is operating at times. | Further assessment | This has been incorporated into the revised T+T LFG Masterplan. Note the revised maximum modelled capture rate is slightly lower than the previous value. The Air Quality report has not been updated to reflect this change. It has continued to use the slightly higher value as this is a somewhat conservative approach. | Yes - see T+T Masterplan update 30/09
38. The LFG model from 2021 (T&T) refers to the landfill closing in 2026. However, the Design report and LDMP indicate that the landfill will operate longer. It is also noted that the design report estimated the void space available for waste filling based on June 2022 data (which is later than the LFG model). a) Are the LFG model generation rates representative of the landfill life and tonnages proposed in the LDMP and design report? b) If not, provide comment on what the impact the capacity of the LFG treatment system (as per above). | Further assessment | This has been incorprated into the revised T+T LFG Masterplan. This is a September 2023 update of the Masterplan submitted with the GI consent application documents. | Yes - see T+T Masterplan update 30/09
39. Section 3.5.3 of design report states: “it is not considered likely that concentrations of CO2 in the gas wells pose a risk”. a) Provide an explanation on what “risk” is being referred to here, and why is it considered low. b) Please confirm if this statement based on a LFG risk assessment, conceptual site model or some other assessment. | Further assessment | a) The purpose of the perimeter gas monitoring wells is to detect any off site movement of LFG. The wells are located along the landfill boundary between the landfill and the nearest residential properties. To date, methane has not been detected in the wells since their installation in May 2020 other than a very low concentration of 0.1% v/v on two occasions in July and October 2020. These were very low concentrations at the measuring instruments minimum detection limit and were not considered significant. The available data from the perimeter gas monitoring wells indicates that off-site movement of LFG is not occurring from the site. This in turn indicates that the likelihood of adverse impacts from migrating subsurface LFG upon the adjacent residential receptors is considered low. b) A formal risk assessment has not been completed for the site. However, a number of site characteristics make the likelihood of adverse impacts from migrating subsurface LFG upon the adjacent residential receptors low. These include: i) The site is underlain by low permeability marine sediments with a high groundwater table. This precludes the movement of LFG through the underlying strata. ii) The site is almost completely surrounded by the leachate collection system. This includes a trench and dewatering pumps which maintain a groundwater/leachate hydrological divide that ensures leachate seepage from the landfill is collected and directed to the Green Island Waste Water Treatment Plant. This trench will also act as a barrier to LFG movement off site through the sub soil. iii) The continued expansion and operation of the LFG collection system combined with capping of the landfill further reduces the likelihood of offsite LFG movement. iv) The regular LFG monitoring program. | Yes
40. Section 4.5.1 refers to horizontal LFG collection pipes. a) Please confirm if these are collection pipes (perforated) or transmission pipes (e.g. header pipes). b) Provide comment on whether temporary horizontal LFG collection wells been considered in the active cells to enable LFG collection prior to installation of vertical LFG wells. | Further assessment | This has been incorporated into the revised T+T LFG Masterplan | Yes - see T+T Masterplan update 30/09
41. Provide details on the vertical LFG collection pipes including but not limited to the diameter, bore annulus and backfill, depth relative to the waste mass and unsaturated length of well screen. | Further assessment | This has been addressed in the updated T+T LFG management letter dated 21/09/2023 | Yes - see T+T letter 21/09
42. Section 2.5.2 of LFG Masterplan (app C of Design report) states that flaring is not the primary LFG treatment method, so NES Air Quality requirements relating to flares do not apply. It is assumed this is a reference to Regulation 27 which requires that if flaring is the primary treatment method, then a candlestick flare can be a backup flare only, and not the primary flare. a) Please provide the treatment volumes of the LFG engine and the candlestick flare to assess which is the primary treatment method. b) If LFG treatment efficiency increases (refer earlier questions), is the engine capable of being the primary treatment method? | Further assessment | This has been incorporated into the revised T+T LFG Masterplan | Yes - see T+T Masterplan update 30/09
44. As per WasteMINZ Technical Guidance, the objectives of LFG systems should be to reduce LFG hazards, minimise odour and minimise greenhouse gas emissions. Has the effectiveness of the LFG system at achieving these objectives been assessed (e.g. through monitoring, development of CSM, LFG risk assessment)? | Further assessment | This has been incorprated into the revised T+T LFG Masterplan | Yes - see T+T Masterplan update 30/09
45. It appears there are existing LFG wells in areas that are not yet filled and capped. a) Provide comment on how these will be managed when works are occurring around them. b) Provide comment on how these will be maintained during works including but not limited to how they will be extended higher as required and replaced as needed | Further assessment | This has been addressed in the updated T+T LFG management letter dated 21/09/2023 | Yes - see T+T letter 21/09
46. Please provide more detail on the staging of installation of future LFG wells, particularly noting that the landfill may operate for some years yet. Provide specific comment on whether there will be large areas of the landfill not extracting LFG due to the active filling and capping delaying LFG well installation. | Further assessment | This has been addressed in the updated T+T LFG management letter dated 21/09/2023 | Yes - see T+T letter 21/09
48. Section 3.4 of LDMP and section 4.4.2 of Design Report differ on landfill life remaining. Please clarify which estimate is relevant for the landfill, particularly noting the low estimate of landfill life in the design report is still higher than the LDMP. | Desktop | This is correct. The current updated LDMP reflects the design life for the currently consented landfill shape. When the consent is granted the LDMP will be updated to refelect the revised landfill shape and the revised landfill life. Note this is litsed in Appendix 18 LDMP Summary of Recommended Changes as a matter that will require addressing.

## Landscape and Visual Amenity
Green Island Landfill Section 92 Response Landfill Tranche 4
Landscape, Natural Character and Visual Effects
Expert - Sue MacManaway, Boffa Miskell, Christchurch
Section 92 request | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
Landscape and visual amenity
49. Please provide and reference (in the assessment) photographs taken from within the site to demonstrate the comparative existing landscape character, and as a relevant basis for effects discussion. These should also illustrate reciprocal views to relevant surrounding locations. | Fieldwork | Discussed with ORC peer reviewer at meeting on 25 September 2023 and agreed screenshots from the model would be sufficient to provide the additional information needed. | Yes - see attached screenshots
50. Photographs and graphics should set out the existing and proposed extent of the borrow pit area, with accompanying reference in text (Figure 7 - Staging Plan does not clarify this point). Please amend to incorporate extents of the borrow pit. | Further assessment | Discussed with ORC peer reviewer at meeting on 25 September 2023 and advised that the staging plan included in the LAV graphic supplement (Figure 7 ) showed the full extent of the borrow pit up to closure of the landfill. As the borrow pit is an operational feature and would be used as needed it wasn’t practical to further define its staging and, therefore its visual effects, beyond the assessment already provided. Progressive grassing of the pit is proposed to mitigate visual effects. Pit areas will remain grassed until the clay is needed for capping. | Yes
52. Please provide a visual simulation for Viewing Location E, noted in the assessment as having higher visual effects than locations A and B from where simulations are provided. | Fieldwork | Discussed with ORC peer reviewer at meeting on 25 September 2023 and agreed screenshots from the model would be sufficinet to provide the additional information needed. | Yes - see attached screenshots
55. Some relevant views from dwellings are closer to the site than their representative public viewpoints provided. Further focus has been given in relation to Clariton Avenue properties. Please provide further consideration in relation to other Viewing Areas/Locations. As observed while visiting the site and surrounds, this is particularly sought for properties in the vicinity of Blanc Ave, Wavy Knowes Drive and Paterson Street (and roads just above). ZTV analysis may be necessary to address the viewshed more broadly, and through development stages. | Fieldwork | Discussed with ORC peer reviewer at meeting on 25 September 2023 and agreed screenshots from the model would be sufficinet to provide the additional information needed. | Yes - see attached screenshots
56. The Vegetation Management and Restoration Plan’ is referenced in the text as both being proposed and recommended. Please provide a copy of this document to ascertain its effectiveness for mitigation and enhancement. | Fieldwork | Proposed consent condition has a 12-month timeframe to complete the VRMP as it requires baseline condition assessment of the existing vegetation and significant engagement with mana whenua (and other stakeholders inc the local community). It is therefore proposed that a DRAFT 'Vegetation Management and Restoration Plan Framework' document is provided. This framework sets out the proposed structure for the VMRP and provides suggested indicative content which will be finalised in accordance with the proposed consent condition. Please note that the requirement for the LVMP is related to the LAV assessment of effects only and is not considered a requirement of the ecological effects assessment. However, the framework comments on the ecological values of the site as this is anticpated to be of interest to mana whenua and is in accordance with the Cultural Impact Assessment. This will be discussed further with mana whenua following granting of the consent. | Yes - please see attached draft Vegetation Restroration Management Plan Framework document prepared by Boffa Miskell (30 September 2023).
57. a) Please provide a concluding statement on the appropriateness of the application to be integrated into this landscape setting (with reference to Te Tangi a te Manu). b) Please clarify the concluded finding on landscape effects, described as limited. | Desktop | It is considered that it is the role of the AEE to provide a conclusion of the appropriateness of the application to be integrated into this landscape setting. However, we have provided a concluding statement which confirms the level of effect in the context of the landscape values and the statutory context with reference to the table on p151 of Te Tangi a te Manu. | Yes - please see attached updated conclusion.

## Air Quality
Green Island Landfill Section 92 Response Landfill Tranche 4
Air quality report
Expert - Peter Stacey
Section 92 request | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
Odour
83. Page 11 of the Air Quality Assessment includes a statement that the document is in draft form. Please confirm that this figure (Figure 2.4) is the final version and can be relied upon. | Desktop | The draft disclaimer is an error. This has been adjusted and a revised copy of the report is attached. | Yes - see updated Air Quality report dated 29/09
106. A mitigation objective is stated to be keeping the working face size to a minimum. a) The Design Report recommends no greater than 500m2 “for the majority of the time” – is this achievable and if so, when will it be achieved? If it is not achievable, please explain why and describe how efforts will be made to achieve this recommendation as far as practicable. b) The current operational plan requires a maximum 900m2 working face size (as stated in Section 6.1.1). For context, what was the size of the working face on the day of the site visit (we note that the reason for the current working face size was explained during the site visit, this question relates only to what the actual size was)? c) The proposed consent condition for the working face size is “must not exceed 900m2 , except under some conditions it may be expanded to 1200m2 ”. o This is inconsistent with the Design Report recommendation for 500m2 which is for fire risk mitigation; please propose how the recommendation from the Design Report can be reflected in the consent conditions. o One of the allowed conditions for the expanded working face of 1200m2 is “where landfill gas escape from underneath the day’s refuse, and odour from the day’s refuse are unlikely”. Please explain how this condition would be assessed and interpreted. d) There is a separate recommendation to limit the tip face width to 30m. Please explain why this limitation is needed in addition to the working face area restrictions. | Further assessment | Please note the reference to a 500m2 area in the Design Report is an error and has been addressed in the 30 September update of the report. An updated LDMP has also been provided. However, please note this LDMP is for the existing landfill operation under the existing consented regime. If consents are granted for Green Island as proposed then the LDMP will be updated to reflect the new consented regime and issues such as the size of the operational face will be addressed in the LDMP at that time. To capture what changes may be required Appendix 18 has been prepared which lists the proposed LDMP changes if consents are granted. A copy of the updated Appendix 18 has been provided along with the updated LDMP. a) this was an error and has been edited b) We believe the face was >1,000 m2 on the day of he site visit c)The design report is now consistent with the draft consent conditions, In regard to how the conditions are assessed and interpreted with respect to expanding the workface it is dependent on a large number of factors including: o Weather – wind, barometric pressure. o Location of tipface in respect to historically placed waste. o Nature and quality of a daily / intermediate cover adjacent to tipface. o Nature of waste being placed on the day in terms of odorous nature and permeability. o Configuration of landfill gas network around tipface (including solar flares). o Performance and reliability of landfill gas network in the immediate area. d) After discussion with the DCC landfill teams it appears there is not specific need for any constraint on the width of the work face. It has been convention rather than any requirment to work with a 30 m wide work face. We have adjusted the Design Report text and the proposed consent conditions to refelect this. | Yes
108. “Regular odour scouting” is identified as a proposed mitigation measure for irregular odorous activities. a) Please describe the methodology that will be used for this odour scouting, and whether it will be used regularly or just for irregular loads. Additionally, provide comment on whether the odour scouting can be implemented quickly enough when a load is received? b) Provide confirmation on whether there is any odour scouting carried out now? If so, please provide further information about this including methodology, frequency, and results. | Desktop | a) Odour scout training will be completed by on site staff. Training will be in accordance with the guidance provided in the Ministry for the Environment Good Practice Guide for Assessing and Managing Odour (2016). Procedures will be generally as follows: - Initial upwind observation. - Starting at the furthest extent of a potential plume make downwind observations in a zig-zag pattern moving towards the potential source of odour. - Methodology will be based on the "Dynamic Downwind Surveillance" methodology described in the Draft Odour Surveillance Guidance produced by EPA Victoria. - At each odour observation, the odour scout records the odour intensity (on a scale of 0-6) and character (from a large range of descriptions) every 10 seconds for a period of 10 minutes. - A range of other parameters are also recorded at the site to characterise conditions during monitoring. Given the trained staff will be on site, it is expected that this process can be implemented quickly if an issue arises or a problematic load has been received. These are in addition to the notification requirements for carriers bringing loads, and the ability of the booth and landfill staff to hold back problematic loads if they need to. The protocol will be included in the LDMP if consents are granted (see updated Appendix 18) b) No odour scouting is currently undertaken. | Yes - see updated Air Quality report dated 29/09