## Leachate and Stormwater
Consent Application RM23.185 Green Island Landfill
ORC request for further information section 92(1)
Auditor James Elliott/SLR
Technical expert - Allen Ingles
Item | ORC Request for Further Information | DCC Response
1 | Please explain why remedial works to repair the leaking eastern culvert will only be undertaken “within 12 months of consent being granted for ongoing operation, and if followup or additional works are required, then within three years” when this is a known discharge of leachate into the environment? | This work is now underway and is expected to be completed by the end of March 2025. This has been updated in the reports
2 | Please confirm the classification and fate of surface water runoff from intermediate cover areas. | As set out in the Surface Water Report, surface water runoff from intermediate cover is currently treated as leachate and directed to the leachate collection system.
3 | Please confirm whether the northern leachate pond is currently lined, and if not, whether lining of this pond is proposed as part of this application. Please provide justification for your answer | The Northern Leachate Pond is lined. The Surface Water Report update provides a more detailed description of the NLP
4 | It is noted that in section 4.1.3 of the Surface Water Report that leachate may overflow from the northern leachate pond to perimeter swales and discharge to Kaikorai Stream. Please provide an assessment of the effects of the discharge of this untreated leachate to the environment. In your answer, please specify what is meant by “prolonged high rainfall” in the context of the site. | This has been provided in the updated Surface Water Report
5 | With respect to the combining of water categories on site, the Surface Water Report (Section 4.1) states that “it is acceptable for … clean and sediment laden waters to be directed to the leachate system. The high proportion of catchments currently being directed to the leachate system without causing issues is proof of this”. It is unclear what “withoutcausing issues” is referring to. Please define what an “issue” is in this context and provide the relevant evidence that an “issue” hasn’t occurred. | This has been provided in the updated Surface Water Report
6 | In light of the recommendations of this audit, please confirm whether any active extraction of leachate is proposed at the site. Please provide an explanation for your answer and, if active extraction is proposed, please describe the circumstances in which it will be undertaken and propose a condition(s) of consent reflecting this. | Active extraction of leachate is discussed in the Geotechnical Report. It is included as a mitigation option to maintain leachate levels within the waste. Pumping from gas wells is considered

## Landfill Gas
Green Island Landfill - Technical Peer Review Worksheets
Landfill Gas - James Elliot/SLR
Project Specialist -
Item | ORC Request for Further Information | DCC Response
7 | Please specify the timing of the installation of new LFG extraction wells. Your answer should explain why you consider that this timing is appropriate.Refer to Question 6 (Section 3.2.3, bullet point 6) for more details | Tonkin and Taylor have prepared a updated Landfill Gas Master Plan which contains this information. A copy is included with the s92 responses
8 | Please undertake a landfill gas risk assessment (LFGRA) for the site. This should address the points raised in Questions 2 and 6 of Mr Elliott’s memorandum | Tonkin and Taylor have completed a LFGRA - a copy is included with the s92 responses

## Capping and Liner
Green Island Landfill - Technical Peer Review Worksheets
Capping and Liner - James Elliott/SLR
Project Specialist -
Item | ORC Request for Further Information | DCC Response
9 | Please confirm whether or not a piggyback liner will be adopted at this site. | A "Piggy Back" liner is not propsoed for this site.
10 | Please provide the assessment (referenced in the Design Report) that indicates that a piggyback liner does not provide any additional benefits (compared with the existing leachate trench). | Section 4.4.3 describes in detail three key risks associated with the possible construction of a "Piggy Back" liner at this site and why this option was considered and discounted. An assessment of any benefits compared to the existing leachate trench has not been undertaken and is not considered warranted.
11 | Please provide additional information on the “physical and landscape constraints” that have resulted in the proposed 2% grade of the landfill cap. | See Attached Response to Question 11 | Rachael/Maurice - note we have a WORD file with these responses in the folder…
12 | Was the impact of a composite lined cap modelled to assess if this would be more effective in reducing leachate head? In relation to the statement (response to s92 question 8 – see summary spreadsheet) “the capping profile was subject to infiltration modelling which was deemed suitable” please advise how and who deemed it to be suitable. | A composite liner was not assessed. The landfill cap design is consistent with the capping design developed in 2021 and reported in the GHD Capping Report. The report identified and assessed on-site and nearby sources of cover materials to achieve the capping design specifications. This assessment was undertaken to confirm the availability of source material for capping purposes and to appropriately define testing and validation specifications for capping material quality and its placement and compaction. The 2021 review has considered information available from the prior borrow area investigations undertaken by Adams Geotechnical Ltd. The following factors were reviewed and considered: • Volume of available material • Suitability of material to meet requirements outlined in the MfE guidance document for • landfill closure • Assessment of suitability of a stockpile of soil (the 4000 m3), to be used as topsoil • Heterogeneity of available material and potential operational limitations • Recommended compaction standards This 2021 assessment provides the technical background regarding the “suitability” of the capping material. The 2023 GHD technical report has provided a further evaluation of the capping materials performance in relation to leachate generation. This has included sensitivity testing reported in Appendix F.
12A | Section 3.2.4.2 of the review comments notes that "It appears that the cap profile does not strictly meet the minimum recommended final cover requirements detailed in the WasteMINZ Guidelines. However, the reduced thickness of the intermediate cover layer, and the absence of a subsoil layer and a membrane/GCL, may still be appropriate, subject to further assessment of potential for leachate to impact the surrounding environment. If leachate is found to be impacting the surrounding environment such that additional mitigation/remedial measures are required, then the cap profile may need enhancement to further reduce the potential leachate generation rates, and reduce potential impacts of leachate on the surrounding environment" While the reviewer has not specifically asked for a response on this issue we haev provided a propsoed approach. | See Attached Response to Question 12A

## Landfill Fire
Green Island Landfill - Technical Peer Review Worksheets
Landfill fire - James Elliott/SLR
Project Specialist -
Item | ORC Request for Further Information | DCC Response
13 | Please provide a Fire Risk Assessment either as a standalone document or as a revision of the existing Fire Management Plan. The Fire Risk Assessment should address the matters raised in Question 8 of Mr Elliott’s memorandum. | A Fire Risk Assessment has been prepared by GHD and is included with the s92 response information

## Groundwater Quantity & Quality
Green Island Landfill - Technical Peer Review Worksheets
Groundwater Quantity and Quality - Tim Baker and Anna Lukey/SLR
Project Specialist -
Item | ORC Request for Further Information | DCC Response
14 | Please explain whether the recently installed wells (RM22.511.01) will form any part of future groundwater quality monitoring programme. Please explain your answer. | A revised Groundwater Report has been prepared that addresses this question and provided with the s92 response.
15 | To provide a more accurate representation of groundwater direction/elevation at the site, please provide an updated analysis by surveying in all historic monitoring wells on site. If this analysis leads to any new information or conclusions, please also update any assessment that relies on the description of groundwater direction/elevation, including the Groundwater Conceptual Site Model. | A revised Groundwater Report has been prepared that addresses this question and provided with the s92 response.
16 | Please provide a revised description of the use of groundwater, including the sensitivity of the groundwater resource, in the area surrounding the landfill by taking into account the 49 bores identified through this s92 process. Please also provide an assessment of the potential adverse effects on these groundwater users. | A revised Groundwater Report has been prepared that addresses this question and provided with the s92 response.
17 | It is the recommendation of both Mr Baker and Ms Lukey that additional downgradient groundwater monitoring wells, including deeper wells, are required to determine the potential adverse effects on groundwater. These wells would enable additional information to be collected to support the nature of the groundwater beneath the site (elevation and direction of groundwater flows, presence or absence of an upward hydraulic gradient) and to support the subsequent conclusions drawn in the application as to the effectiveness of the leachate interception trench and the likelihood, and impacts of, any offsite migration of leachate. It is also the recommendation of Mr Elliott (Landfill Design) that further assessment be made as to the impacts of leachate on the surrounding environment in order to assess the adequacy of several landfill design elements. Taking into account your updated assessment of the sensitivity of the groundwater resource, and effects on any groundwater users, please provide a discussion that considers and evaluates the benefits of installing these additional monitoring wells now at the locations suggested in these memos, versus after consent is granted. Your answer should include a risk assessment, should address all of the concerns raised in Mr Baker and Ms Lukey’s memos, should discuss how the proposed monitoring network meets the WasteMINZ guidelines,1 and should include an outline of an adaptive groundwater management plan, if your analysis concludes that installation of the wells should be after granting of consent. | This issue has been addressed in the revised Groundwater Report. This includes the addition of a deep monitoring well (BH103). The reviewers are also referred to the Human Health and Environmental Risk Assessment.
18 | Please provide an assessment of the impact that groundwater quality will have on the expected recreational land use and potential future receptors. | A revised Groundwater Report has been prepared that addresses this question and provided with the s92 response.
19 | Please confirm whether or not you agree to a consent condition requiring provision of a Groundwater Monitoring and Contingency Plan, which includes at least the below four items (listed in Mr Baker’s memo): • Details of all monitoring well construction (depth, elevation, material, logs) • A sampling and analysis plan, including the sampling methodology to be followed. • A plan for the installation of additional boundary wells, and new deep transect wells, including the proposed depths, construction, and timing of installation. • Other items as addressed in the Groundwater Quality memo. | A revised Groundwater Report has been prepared that addresses this question and provided with the s92 response. It is noted that rather than developing a separate Groundwater Monitoring and Contigency Plan, as required by proposed general condition 49, monutoring requirements will be contained within the updated Landfill Development Management Plan required by proposed general condition 12 (pre-closure), and Landfill Closure Management Plan required by general condition 16 (post-closure).

## Surface Water Quality
Green Island Landfill - Technical Peer Review Worksheets
Surface Water Quality - Claire Conwell/SLR
Project Specialist -
Item | ORC Request for Further Information | DCC Response
20 | The surface water report assumes that all the leachate generated on site is collected via the leachate trench and that no leachate is migrating into the surrounding surface water, on the basis that there is no evidence of leachate contaminants being present in surface water in exceedance of relevant guideline levels. As such, the application does not contain any assessment of the impacts of leachate on the surface water receiving environment. It is the opinion of Dr Conwell, as well as Mr Elliott, Mr Baker, and Ms Lukey, that a more comprehensive assessment is required into the overall weight of evidence approach to this assessment of effects. Therefore, please provide an assessment of the potential adverse effects of leachate on surface water in the receiving environment. This assessment should: • Link to the answers provided in response to the questions in the landfill design (leachate) section and the groundwater section. • Address all of the concerns raised in Dr Conwell’s memo, and in particular should include a thorough assessment of cumulative effects on surface water, which takes into account contamination attributable to the landfill, any measurable or known contribution of contaminants from the upstream catchment, and discussion on the way in which contribution of contaminants from the landfill may be distinguished from other inputs including any uncertainty in this assessment. • Take into account the results of the ecotoxicological monitoring that is currently being undertaken and include copies of analytical results and interpretation of results. | The Surface Water and Groundwater Reports have been updated to address the issues raised by the reviewers. Cumulative effects have also been discussed in the revised reports. The reviewer is also refereed to the Human Health and Environmental Risk Assessment.

## Surface Water
Green Island Landfill - Technical Peer Review Worksheets
Surfacewater - Claire Conwell/SLR
Project Specialist -
Item | ORC Request for Further Information | DCC Response
21 | Please provide the results for any surface water quality sampling in which samples were tested for dissolved zinc. | This has been included in the updated Surface Water Report
22 | Please undertake further statistical analysis, as described in question 8 of Dr Conwell’s memo, of the available water quality data for the purpose of providing further evidence to support the conclusions as to adverse effects made in section 5.1 of the Surface Water Report. | Further analysis of the available data has been provided in the updated Surface Water Report
23 | Please confirm whether or not you agree to a consent condition requiring provision of an adaptive management plan for the surface water monitoring programme that includes at a minimum all of the elements listed in Question 3 of Dr Conwell’s memo. | We have not included an adaptive management approach in the monitoring recommendations. We have included the recommendation that the Human Health and Environmental Risk Assessment is reviewed and updated after a further three years of monitoring. This may drive the need for adaptation of the monitoring program.

## Ecology
Ecology - Elizabeth Morrison/SLR
Project Specialist - Tanya Blakely, Boffa Miskell
Item | ORC Request for Further Information | DCC Response
24 | Taking into account your answers to the questions in the landfill design, groundwater, and surface water sections, and the results from the additional ecotoxicological investigations currently being undertaken, please provide an updated assessment of effects on aquatic ecology. Your answer should include a thorough assessment of the potential cumulative effects and should link to your responses to similar questions asked in other sections above. | The ecology report presents findings of aquatic ecology values, including sediment quality (concentration of contaminants), at sites upstream of and within / downstream of the landfill. Contaminant concentrations in sediments at GI3 and GI5 were never higher than those recorded at either or both of the upstream control sites, indicating that these contaminants are present in higher concentrations and likely coming from up-catchment sources. The Ecological Impact Assessment (particularly Section 5.7) has been updated to more clearly discuss that contaminant concentrations in stream bed sediments are always less than one or both of the upstream control sites (GI1 & GI2) and (except for lead and zinc, and DDT and its DDD / DDE metabolites) are below the DGV threshold at GI3 and GI5 (sites adjacent to the landfill).
25 | In light of Cawthron’s recommendations for ecotoxicology investigations, Ms Morrison has recommended that further ecotoxicology investigations are implemented as part of an adaptive management plan, in the event that results from other monitoring, such as groundwater, surface water or ecological monitoring, indicate that more detailed investigations are required. As such, please propose conditions of consent that set out the circumstances in which ecotoxicological investigations would be undertaken, how this relates to/aligns with any proposed monitoring for groundwater or surface water and how this information would be used to inform other monitoring or adaptive management processes. | The Kaikorai Stream and estuary catchment is highly impacted by current and historical landuse, which is reflected by the tolerant freshwater communities found in the freshwater habitats. Because of this, further ecological monitoring has not been suggested as determining cause and effect relationships of any changes in communities will be masked and likely indiscernable. Further to this, surface water and groundwater monitoring to date shows that leachate is contained and managed by the leachate treatment system, with no detected landfill derived contaminants entering Kaikorai Stream. Therefore, it is more appropriate to continue water quality monitoring at the current and proposed monitoring sites. This includes both surface water and groundwater monitoring. In the event that a sustained exceedance in the surface water quality is detected, as compared to the proposed guidelines and upstream 'reference' sites, follow up investigations would be triggered to determine the source of landfill derived contaminants entering Kaikorai Stream. This has been reflected in draft general consent conditions 47 and 48.

## Landscape & Visual
Green Island Landfill - Technical Peer Review Worksheets
Landscape & Visual Assessment - Rachael Annan/SLR
Project Specialist - Sue McManaway, Boffa Miskell
Item | ORC Request for Further Information | DCC Response
26 | Please confirm whether or not you agree to adopt the recommendation in Ms Annan’s memo (end of page 5) for an independent technical review of the following aspects of the (final) Vegetation Management and Restoration Plan: • The effectiveness of the management plan in relation to ecological restoration and habitat health; • Alignment with mana whenua outcomes sought derived from partnership discussions and the CIA. • An effective approach to landscape character and visual amenity outcomes for surrounding residents (which draws on community consultation), including review of planting plans and schedules; and • Planting implementation shall be signed off by a landscape architect, or other suitably qualified expert, with subsequent monitoring of vegetation health (and any replacement required). It is anticipated that an arborist report will be provided (and inform the Vegetation Management and Restoration Plan) regarding the health of existing vegetation. | Proposed consent conditions 41 - 42 set out the proposed process for developing and confirming the final VRMP. The plan is required to be developed in consultation with Te Rūnanga o Ōtākou who will provide direct input to ensure mana whenua outcomes are appropriately incorporated. The plan is required to be provided to ORC for certification, and we note that as part of that certification process ORC is entitled to seek appropriate technical review and input.

## Air Quality
MASTERSPREADSHEET: PCG USE ONLY
Green Island Landfill - Technical Peer Review Worksheets
Air Quality - Tracy Freeman/Jacobs
Project Specialist -
Item | ORC Request for Further Information | DCC Response
27 | Please confirm whether or not you agree to adopt the consent conditions as proposed in Ms Freeman’s memo. | The following resonses are provided - Monitoring of sulphide content of the biogas feed. Response: H2S will be collected as part of regular monitoring at Gas Engine or Flare Inlet. Monitoring requirements will be detailed in the updated Landfill Development Management Plan as required by draft disharge to air consent condition 20. Monitoring of gas flow rates to the engine and flare. Response: this is addressed in draft discharge to air consent condition 15. Monitoring of stack discharges from the engine. Response: We do not believe continual monitoring of the engine discharge is warranted. The atmospheric dispersion modelling demonstrated that the off-site contributions of air pollutants from the engine are well below the relevant air guidelines and standards. Monitoring of odour at the site boundary and at sensitive receptors by odour scouts, both by independent contractors and by site-staff, with adaptive management of on-site operations and mitigation measures in response to monitoring outcomes. Response: Odour monitoring requirements will be detailed in the updated Landfill Development Management Plan as required by draft discharge to air consent condition 5. Site staff are being trained in formal odour monitoring procedures. With the need for regular monitoring and the ability to respond quickly to any odour complaints the Council proposes to focus on utilising site staff as a priority with the use of independent contractors only if site staff are unavailable. Restrictions on the size of the working face. Response: This is addressed in draft general condition 26. Periodic independent review of the landfill operation. Response: We do not see the need for a further condition requiring an independent review. The Landfill Development and Management is reequired to be reviewed by the consent holder annually as per draft general condition 15, with any amended plan provided to the ORC for recertification in accordance with draft general condition 4. As part of that certification, ORC has the ability to seek independent technical peer review. ORC also has the ability to intiate a formal review of the consents under s128 of the RMA as per draft general condition 57. Maintaining wind monitoring at the site: Response: A Meteorological station has been established at the site for a number of years, and is required to be retained under draft general condition 37. Ensuring that the full range of mitigation measures detailed in the AQ Report Rev02 are carried through into the LDMP. Response: The full range of measured will be carried into the updated LMDP required by draft general condition 14.
28 | Please provide an updated assessment of odour effects which specifically takes into account expected odour emissions from the Organics Receivals Building (ORB, application RM23.571) on the site. Note that the ORB application was processed on the basis that organics processing was an activity captured by the existing landfill consents and their replacements (being this application RM23.185). Therefore, I consider that the odour effects of the ORB must be addressed here. | An updated version of the Air Quality Report has been provided that includes the ORB in the assessment
29 | Please explain whether the flare at the GIWWTP can be regarded as a principal flare for the purpose of the NES-AQ Regulation 27, and whether the proposed new flare complies with the design requirements in Regulation 27. | The flare at GIWWTP does not meet the requirements for a principal flare set out in NES-AQ Regulation 27(2). However, as the gas is primarily used as a fuel for generating electricity (26(2)(b)(ii), Regulation 27(2) does not apply. The flare at GIWWTP is used as a backup to the destruction of gas using the LFG engine and meets the requirements of Regulation 27(3). GHD does not consider the intent of Regulation 27 is for landfill operators to be required to have three forms of gas disposal infrastructure (i.e., LFG Engine, Primary Flare, and Secondary Flare) and that the LFG Engine and backup flare utilised at GIWWTP are appropriate controls to minimise greenhouse gas emissions
30 | Please provide a tracked changes version of the Air Quality Report. | Provided