## Landfill Design and MgMt
Green Island landfill - Section 92 Responses Tranche 3
Landfill Design and Management
Contacts - NICK ELDRED, P LANDMARK
Technical reports - LANDFILL DESIGN REPORT, LDMP
Section 92 request
Landfill Design | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
15. Please confirm if there is a maximum thickness value for the layers mentioned in questions 12-14 to ensure compaction is achieved throughout the relevant cap layer. | Desktop | We would like to discuss this issue with the ORC Technical Auditors for clarification. | No - requires ongoing discussion with ORC technical auditors. Response will be sent through as part of Tranche 4 due 30 September 2023

## Landscape and visual Amenity
Green Island Landfill Section 92 Response Landfill Tranche 3
Landscape, Natural Character and Visual Effects
Expert - Sue MacManaway, Boffa Miskell, Christchurch
Section 92 request | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
Landscape and visual amenity
49. Please provide and reference (in the assessment) photographs taken from within the site to demonstrate the comparative existing landscape character, and as a relevant basis for effects discussion. These should also illustrate reciprocal views to relevant surrounding locations. | Fieldwork | Noted. Additional interpretation photos to be provided. | No - delayed until Tranche 4 with landscape assessment report update and revegetation management plan.
50. Photographs and graphics should set out the existing and proposed extent of the borrow pit area, with accompanying reference in text (Figure 7 - Staging Plan does not clarify this point). Please amend to incorporate extents of the borrow pit. | Further assessment | Noted. Plans, including staging plan, and text can be amended to included extent of borrow pit. | No - delayed until Tranche 4 with landscape assessment report update and revegetation management plan.
52. Please provide a visual simulation for Viewing Location E, noted in the assessment as having higher visual effects than locations A and B from where simulations are provided. | Fieldwork | Noted. Additional visual simulation able to be prepared provided we can find a suitable viewpoint from public property. | No - delayed until Tranche 4 with landscape assessment report update and revegetation management plan.
53. Figure 3 - Topography Plan (of the graphics supplement) requires annotation of landscape features as described in text, p. 16-17. For clarity, please also provide LIDAR contours (or similar) for the surrounds illustrating comparative information for the landscape setting. The technical auditor notes the final contours shown on Fig 3 within the assessment, however this is too small to view of the surrounding area. | Further assessment | Noted. Figure 3 - Topography Plan will be annotated. Contours of landscape setting will be illustrated. | Yes - see attached plan.
55. Some relevant views from dwellings are closer to the site than their representative public viewpoints provided. Further focus has been given in relation to Clariton Avenue properties. Please provide further consideration in relation to other Viewing Areas/Locations. As observed while visiting the site and surrounds, this is particularly sought for properties in the vicinity of Blanc Ave, Wavy Knowes Drive and Paterson Street (and roads just above). ZTV analysis may be necessary to address the viewshed more broadly, and through development stages. | Fieldwork | Noted. Additional visual simulations can be prepared from publicly accessible viewpoints, representative of properties in the vicinity of Blanc Ave, Wavy Knowes Drive and Paterson Street. | No - delayed until Tranche 4 with landscape assessment report update and revegetation management plan.
57. a) Please provide a concluding statement on the appropriateness of the application to be integrated into this landscape setting (with reference to Te Tangi a te Manu). b) Please clarify the concluded finding on landscape effects, described as limited. | Fieldwork - ZTV analysis can be a useful tool to inicate potential visibility. However, as described in Te Tangi a te Manu, they have shortcomings, including that they typically predict potential visibility based on topography alone - whereas visibility of the Green Island landfill is highly influenced by vegetation on the site. | A concluding statement which confirms the level of effect in the context of the landscape values and the statutory context with reference to the table on p151 of Te Tangi a te Manu, can be provided, however it is considered that it is the role of the AEE to provide a conclusion of the appropriateness of the application to be integrated into this landscape setting. | No - delayed until Tranche 4 with landscape assessment report update and revegetation management plan.

## Ecology
Green Island Landfill Section 92 Response Landfill Tranche 3
Ecology
Expert - Tanya Blakely, Boffa Miskell
Auditor - Elizabeth Morrison
Section 92 request - ecology | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
77. Please provide an ecological site features plan that clearly shows the ecological areas on the site including ecosystem types and all water bodies within the designation. There were water bodies observed on site that were not identified on any of the plans provided or in the ecological report. | Further assessment | Plan can be provided - requires further coordination with GHD surface water expert and further fieldwork | Yes - please see Figure 4 dated 30 August 2023 - Please note that not all water bodies noted in the marked up aerial photograph provided by Elizabeth Morrison are shown in Figure 4, the reasons for this are that: • The “stream remnant” identified on the marked up photograph has been reclaimed by the landfill some years ago; and • The “tributary + artificial drains” idnetified on the marked up photograph are side channels and features of Kaikorai Stream .
78. Please provide a plan that shows the location of the Area of Significant Conservation Value in the DCC 2GP and Regionally Significant Wetland by ORC in relation to the site. If there are plans that show the delineated edge of the wetland in relation to the site this would also be useful. | Further assessment | Plan can be provided but is delayed to Tranche 3 | Yes - please see attached Figure 4 dated 30 August 2023

## Air Quality
Green Island Landfill Section 92 Response Landfill Tranche 3
Air quality report
Expert - Peter Stacey
Section 92 request | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
Odour
102. Complaints by year are graphed in Figure 5.1 of the AQA. Is there any known reason for the complaints in 2018/19 being much higher than in 2020/21? | Desktop | Forty two (42) complaints were received in relation to the Green Island Landfill over the 2018/2019 monitoring year. All of these complaints were in relation to odour. Over this period, fifteen (15) new landfill gas extraction wells were added to the extraction network. The installation of some of these wells required the excavtion into and exposure of historical waste material, resulting in odour releases. In addition to these works, odour complaints were lodged when sludges were received from the various Waste Water Treatment Plants (WWTP). Improvements have been made in the way in which these sludges are managed (covering as soon as possible, adding coffee grinds (now discontinued), etc) since this time period. | Yes