## Landfill Design and MgMt
Green Island landfill - Section 92 Responses Tranche 2
Landfill Design and Management
Contacts - NICK ELDRED, P LANDMARK
Technical reports - LANDFILL DESIGN REPORT, LDMP
Section 92 request
Landfill Design | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
15. Please confirm if there is a maximum thickness value for the layers mentioned in questions 12-14 to ensure compaction is achieved throughout the relevant cap layer. | Desktop | We would like to discuss this issue with the ORC Technical Auditors for clarification. | No - requires ongoing discussion with ORC technical auditors. Response will be sent through as part of Tranche 3 due 31 August 2023

## Leachate and Groundwater
Green Island landfill - Section 92 Responses Tranche 2
Leachate and Groundwater
Contacts - DUSK MAINS, NICK ELDRED, P LANDMARK
Technical reports - GROUNDWATER REPORT, DESIGN REPORT, LDMP
Section 92 request
Leachate and groundwater | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
26. The leachate collection system (LCS) is shown on a number of drawings and with other information about the site shown, it makes it difficult to fully understand the existing and proposed LCS layout. Please provide drawings that clearly show the leachate collection system (both existing and proposed) without other non-leachate collection system details (e.g. contours) for a clearer understanding. | Desktop | An additional drawing was to be prepared as part of Tranche 2 response. Further work is required and will be included with the updated design report to claify the issue. Updated design report to be issued 30 September 2023 | No - will be included in updated design report to be issued 30 September 2023 as part of final S92 tranche of information responses
27.It is noted that the drawings and design report include a variety of terms that seem to be related to the LCS. It appears that some terms may be interchangeable which is confusing for the reader. Please provide updated drawings which use consistent terminology across the drawings and the design report. Some examples of the terms on the drawings legends are; • Dwg G101: o Existing leachate drain; and o Existing leachate drain in waste; • G102: o Existing leachate drain; o Existing leachate drain in waste; o Pipe flow; o Interception trench; o Southern interception trench; and o Extent of new leachate collection system. • C204: o Extent of leachate collection system; o Primary leachate collection drain; o Leachate drainage pipe; o Existing leachate drain in waste; o Existing leachate drain perimeter; and o Interception trench (new). • C304: o Section detail of primary leachate drain; o Interception trench detail; o Primary leachate drain detail; o Design report terms; o Leachate ByPass drain; and o Open swale drain. | Desktop | The Drawings will be reviewed and any inconsistency in terminology addressed on the drawings or through the use of a glossary in design report/edit report to make it consistent. This was to be provided in Tranche 2 however further work is required and will be included with the updated design report to claify the issue. Updated design report to be issued 30 September 2023 | No - will be included in updated design report to be issued 30 September 2023 as part of final S92 tranche of information responses

## Landfill Gas and Design Life
Green Island Landfill - Section 92 Response Landfill Gas and Design Life Tranche 2
Contact - NICK ELDRED
Technical reports - DESIGN REPORT
Section 92 request | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
Landfill gas
Design life
35. Drawing C501 appears to show some Landfill gas wells (LFG) wells on the 1:3 sloped area of the cap in the south west area of the landfill (e.g. Wells GW90, GW91 etc..). a) Provide comment on whether it will be possible to safely install and operate wells at these locations? b) Provide comment on whether these wells will be more susceptible to differential settlement and potential damage due to the steep slope? | Further assessment | The Landfill Gas Report referenced in the application documents was prepared by Tonkin and Taylor in 2021. Tonkin and Taylor have been requested to provided an updated version of this report to reflect both the revised design and closure time line. This will include a review of the LFG well layout. This will require edits to the design report and the drawings. | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
36. Design report states that LFG collection averages 251 m3 /hr, compared to estimated generation rates of over 800 m3 /hr in 2021 and 2022, and estimated LFG collection rates of 648 m3 /hr and 666 m3 /hr in 2021 and 2022 respectively. a) Is there a reason for this large discrepancy? b) Has consideration been given to attempting to improve the collection efficiency? | Further assessment | This will be incorprated into the revised T+T Report | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
37. The capacity of the LFG treatment system seems to be 800 m3 /hr if both the engine and flare are operating at full capacity. This is below the peak LFG generation rate estimated via LFG modelling, although it is above the maximum modelled capture rate of 745 m3 /hr (section 3.3 of LFG Masterplan in Appendix C of design report). If LFG collection efficiency increases, is there potential for a short fall in LFG treatment capacity noting that the WWTP contributes biogas to the engine, and the engine seems to have been down for significant periods in the previous financial year (approx. 1 month in March April 2022; and other periods of a week or more) meaning only the candlestick flare is operating at times. | Further assessment | This will be addresssed based on the outcome of the revised T+T Report | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
38. The LFG model from 2021 (T&T) refers to the landfill closing in 2026. However, the Design report and LDMP indicate that the landfill will operate longer. It is also noted that the design report estimated the void space available for waste filling based on June 2022 data (which is later than the LFG model). a) Are the LFG model generation rates representative of the landfill life and tonnages proposed in the LDMP and design report? b) If not, provide comment on what the impact the capacity of the LFG treatment system (as per above). | Further assessment | See response to Q36 | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
39. Section 3.5.3 of design report states: “it is not considered likely that concentrations of CO2 in the gas wells pose a risk”. a) Provide an explanation on what “risk” is being referred to here, and why is it considered low. b) Please confirm if this statement based on a LFG risk assessment, conceptual site model or some other assessment. | Further assessment | A risk assessment will be incorporated into the revised Tonkin and Taylor Report. | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
40. Section 4.5.1 refers to horizontal LFG collection pipes. a) Please confirm if these are collection pipes (perforated) or transmission pipes (e.g. header pipes). b) Provide comment on whether temporary horizontal LFG collection wells been considered in the active cells to enable LFG collection prior to installation of vertical LFG wells. | Further assessment | This will be addresssed based on the outcome of the revised T+T Report | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
41. Provide details on the vertical LFG collection pipes including but not limited to the diameter, bore annulus and backfill, depth relative to the waste mass and unsaturated length of well screen. | Further assessment | This will be addresssed based on the outcome of the revised T+T Report | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
42. Section 2.5.2 of LFG Masterplan (app C of Design report) states that flaring is not the primary LFG treatment method, so NES Air Quality requirements relating to flares do not apply. It is assumed this is a reference to Regulation 27 which requires that if flaring is the primary treatment method, then a candlestick flare can be a backup flare only, and not the primary flare. a) Please provide the treatment volumes of the LFG engine and the candlestick flare to assess which is the primary treatment method. b) If LFG treatment efficiency increases (refer earlier questions), is the engine capable of being the primary treatment method? | Further assessment | This will be addresssed based on the outcome of the revised T+T Report | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
44. As per WasteMINZ Technical Guidance, the objectives of LFG systems should be to reduce LFG hazards, minimise odour and minimise greenhouse gas emissions. Has the effectiveness of the LFG system at achieving these objectives been assessed (e.g. through monitoring, development of CSM, LFG risk assessment)? | Further assessment | This will be addresssd as part of revised T+T Report | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
45. It appears there are existing LFG wells in areas that are not yet filled and capped. a) Provide comment on how these will be managed when works are occurring around them. b) Provide comment on how these will be maintained during works including but not limited to how they will be extended higher as required and replaced as needed | Further assessment | This will be addresssd as part of revised T+T Report | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses
46. Please provide more detail on the staging of installation of future LFG wells, particularly noting that the landfill may operate for some years yet. Provide specific comment on whether there will be large areas of the landfill not extracting LFG due to the active filling and capping delaying LFG well installation. | Further assessment | This will be addresssd as part of revised T+T Report | No - will be included in updated Landfill Gas Report (by Tonkin and Taylor) to be issued 30 September 2023 as part of final S92 tranche of information responses

## Landscape and visual Amenity
Green Island Landfill Section 92 Response Landfill Tranche 2
Landscape, Natural Character and Visual Effects
Expert - Sue MacManaway, Boffa Miskell, Christchurch
Section 92 request | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
Landscape and visual amenity
57. a) Please provide a concluding statement on the appropriateness of the application to be integrated into this landscape setting (with reference to Te Tangi a te Manu). b) Please clarify the concluded finding on landscape effects, described as limited. | Further assessment | A concluding statement which confirms the level of effect in the context of the landscape values and the statutory context with reference to the table on p151 of Te Tangi a te Manu, can be provided, however it is considered that it is the role of the AEE to provide a conclusion of the appropriateness of the application to be integrated into this landscape setting. | No - requires further discussion with the ORC Technical expert in context of other dicussions needed for Tranche 3 RFI's and also development of Vegetation Restoration Management Plan (VRMP)

## Surface Water Quality
Green Island Landfill Section 92 Response Landfill Tranche 2
Contact -Allen Ingles
Technical reports - Surface Water Report
Section 92 request - Surface water quality | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
59.Please provide an updated site plan that accurately shows the watercourses on-site. There was a water course near the Kaikorai estuary that wasn’t mapped or mentioned in the Surface Water Report. | Desktop | Clarification was sought from the technical reviewer with regards to the location of the water course mentioned in the question. From a review of aerial photos, GHD and the technical reviewer (Eloise Ryan) agreed that the water course (located near well line MW2) is a tributary/channel of Abbots Creek. Based on this, the technical reviewer agreed that an additional plan is not required. | Yes - no plan required on agreement with ORC.

## Groundwater and Flood Defence
Green Island Landfill Section 92 Response Landfill Tranche 2
Contact - DUSK MAINS, ALLEN INGLES
Technical reports - GROUNDWATER, SURFACE WATER
Section 92 request
Groundwater | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
61.The Groundwater report is currently silent on whether there are neighbouring groundwater wells, or use of groundwater in the general area. Please provide commentary on this including commentary on nearby drinking water sources. | Desktop | Bore records and water take consents listed on ORC webmaps were reviewed for a 2 km radius surrounding the site. Two water takes were identified, one upgradient of the site at Blackhead quarry and the other for Maxwells Landfill (Waste management) (see attached figure). Two bore consents were identified, the status for these consents are described as “proposed”. Forty nine bore records were identified in the area of interest, as summarised in below. Well summary • Monitoring / Investigation - 13 well/bores • Dewatering – 1 well/bore (Green Island WWTP) • Domestic / stockwater - 1 well/bore (Proposed – RM14.355.01) • Other - 33 wells/bores (Green Island Landfill investigation bores /monitoring wells ) | Yes - well map attached.
62.Please provide an assessment of local groundwater flow direction/contours, this needs to extend to beyond the site boundary. | Desktop | Both the ORC and New Zealand geotechnical databases were reviewed for groundwater level information. No groundwater level information was available for the area surrounding the site (apart from GILF monitoring well data). The area is not known to have a groundwater resource due to the low permeability of the estuarine sediments and the Abbotsford mudstone. A conceptual groundwater contour map is attached, this shows the groundwater /leachate flow direction from the centre of the landfill out towards the leachate interception trench at the site perimeter. Contour values are based on leachate dip measurements in the gas wells installed within the fill. | Yes - supporting figure attached.
63.Please provide a groundwater monitoring well location map with the location of all monitoring wells clearly marked (including MW9D (lost well)). | Desktop | Figure 2.7 will be updated to include MW9D | Updated Figure 2.7 attached.
67.Provide location of former Kaikorai Stream channel which was within the landfill footprint and advise which (if any) monitoring wells cover off this channel and comment on whether it has been considered as a potential leachate pathway and assessed accordingly through the leachate collection system. | Desktop | The location of the monitoring well lines (comprising MWA,B,C and D) are shown against the 1985 aerial (see Figure attached). Line 6 is located adjacent to the channel (with some uncertainty associated with the georeferencing of historical images). The hydraulic conductivity of MW6C (the well closest to the channel) is similar to other wells in the UKEM with no indication of more permeable materials. The operation of leachate interception trench creates a hydraulic barrier to prevent leachate migration out of the site. Given the proximity to the stream channel it is likely that the leachate trench near Line 6 intercepts a greater proportion of stream water compared to the parts of the trench further from the stream (e.g. Line 3) Between 1985 and 1990 ( Refer to aerials in the landfilling history report, Appendix D of the Groundwater technical assessment), the site access road was built over the former channel but there is no evidence that landfilling encroached on the former channel. | Yes - supporting aerial provided as Q67.
70.The HELP model appears to include just present-day rainfall. a) Please provide commentary on the likely effects of climate change on precipitation, infiltration and leachate generation. b) Please provide appropriate climate change scenarios, or justification why they should not be included." | Further assessment | The HELP model utilises a 50 year stochastic model based on the latitude/location results are presented as an annual average (over the 50 years). Estimated changes in precipitation, temperature and relatively humidity A review of the estimated changes in precipitation, temperature and relative humidity for Dunedin has been undertaken using the NIWA ‘Our future climate New Zealand’ online tool (six-model-average RCP8.5 (high) end-century estimate). This is considered conservative due to the post-closure consent due to expire in 2064. The results indicate approximately a 10% increase in annual mean rainfall between 1995 and 2090, up to 2C increase in temperature and minimal reductions in relative humidity. Climate variability already included within 50-year stochastic climate model The 50-year synthetic weather model considers natural variation in climate, with the 50 year period reporting an average annual precipitation of 754.6 mm, with standard deviation of 93.9 mm. As presented visually in the annual rainfall graph, this demonstrates that annual rainfall greater than the approximate 10% annual increase estimated by end-century as a result of climate change has already been modelled within the existing results for 12 of the 50 years. Worst case scenario for leachate leakage and peak head of leachate above base of landfill are estimated to occur prior to capping of landfill As discussed in Appendix F ( HELP Technical Appendix) of the Groundwater assessment, the results of the HELP modelling indicate that the greatest rates of leachate leakage, and peak head of leachate above the base of the landfill, are estimated to occur during Area D ‘worst case drainage’ scenario (mid-landfill drainage layer of bare soil contoured towards drainage system). After capping of Area D, the rate of leachate leakage and head of leachate above the base of the landfill are both estimated to reduce. As capping of the landfill is proposed to be complete by 2029, only the capped landfill will be subject to the estimated changes in climate. The increase in precipitation as a result of climate change is considered to result in rates of leachate leakage and head of leachate no greater than estimated prior to completion of landfill capping. See attached graph for rainfall comparison | Yes - and rainfall comparison graph provided in Q70.
71.The seep/W modelling considers a 0.5m sea level rise scenario but appears to use input from present day rainfall totals. Please provide commentary on the adequacy of this assessment, or an updated assessment. | Desktop | The Seep/W model incorporates an average rainfall infiltration rate based on the results of the HELP modelling. As discussed in the response to Q70, the projected change rainfall patterns is small (10%) and has already been modelled within the existing results for 12 of the 50 year scenario. Furthermore , as noted in Q70 the modelling of the uncapped section of the landfill will have higher rates of rainfall infiltration and leachate generation than future capped scenarios (with or without climate change). Based on this, changes in rainfall patterns due to climate change are not expected to result in a measurable change in leachate generation and collection. It is considered that sea level rise is the climate change effect with the greatest potential to influence the leachate collection system. The modelling indicated a small increase in leachate collection rates due to the increased water head on the river boundary condition. | Yes
72.Consideration of climate change impacts on leachate generation, sea levels, storm surge and groundwater levels is important. Generally, an assessment should be made in alignment with the National Climate Change Risk Assessment (NZZRA) or local frameworks. Please provide commentary on whether the current assessment of climate change risk on the landfill in in accordance with this, and if not please provide updated assessments. | Further assessment | The Otago Climate Change Risk Assessment, provides summary risk ratings for landfills and contaminated sites, with the key risks relating to: • Sea level rise and coastal erosion • Inland flooding • River erosion The summary risk ratings (up to extreme) consider landfills within the entire Otago region, including historic landfills with no liner, capping or erosion protection. With regards to Green Island Landfill: • Coastal erosion risk is not considered applicable, due to the location. • Sea level rise is expected to result in higher water levels in the Kaikorai Estuary. The effect of sea level rise on the leachate collection system has been modelled in the Groundwater Technical Assessment. Higher river levels are expected to result in a small increase in leachate collection pump rates. • The risk of flooding and river erosion is likely to increase due to higher overall water levels (estuary and river). To address this risk, the applicant proposes to raise the level of the perimeter road berm that runs around the landfill between Kaikorai Stream and the leachate trench by approximately 1.0 m to prevent inundation by surface waters. In addition, any electrical controls or similar devices will be raised above a potential future flood level. This work will be completed at least 6 months prior to final receipt of waste. As noted in response to Q 70 and 71, the risk of changing weather patterns (increased precipitation) on leachate generation and collection is considered to be low. | Yes
73.Section 2.2 (Leachate Management) states that the leachate trench intersects contaminated groundwater seeping from the site. GWQ Monitoring in the D ‘Deep’ wells indicates that leachate indicators (NH4N, As, Fe, B) are present beyond the leachate trench, indicating the potential that trench does not intersect all groundwater. Can you please: a) Provide an estimate of the groundwater flux moving beyond (below?) the leachate trench. b) Provide commentary on likely contaminant loads to the estuary/river. | Further assessment | As noted in the GW assessment, historic waste is present outside of the trench in some areas, this impacts the groundwater quality in some of the wells. In addition the groundwater in the estuarine sediments is thought to be naturally elevated in Ammoniacal-N, iron, and boron due to the depositional setting. Figure 2.12 of the groundwater technical assessment graphically shows the different water types and influence of waste. The modelling and review of monitoring data does not indicate a groundwater flux and /or contaminant load entering surface water. A scenario is presented in Section 3.2.1 of the groundwater technical assessment, demonstrating the effect on surface water quality (Ammoniacal-N concentration) should the trench fail and/or not intercept groundwater/leachate flux to the river. There is no indication that this occurs, as surface water monitoring shows that there are no discernible adverse effects on surface water quality from the landfill activities. | Yes
74.The PFAS Section 2.5.3.3 suggest that PFAS is not migrating beyond the leachate trench yet there are positive Total PFAS concentrations in C & D wells. If this is not from the landfill please provide comment on what is the likely source? | Desktop | PFAS has only been detected in C&D wells located in historic waste materials (outside of the trench). | Yes
Flood defence works
76. Section 5.2 of the Surface Water Report refers to a desktop assessment that was carried out to support the assessment of effects of increasing the perimeter road/bund on flood levels. Please provide a copy of this assessment so that the estimated increases in flood depth reported can be verified. | Desktop | Please refer to attached calculations in Q76 | Yes - calculations are attached as Q76.

## Ecology
Green Island Landfill Section 92 Response Landfill Tranche 2
Ecology
Expert - Tanya Blakely, Boffa Miskell
Auditor - Elizabeth Morrison
Section 92 request - ecology | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
77. Please provide an ecological site features plan that clearly shows the ecological areas on the site including ecosystem types and all water bodies within the designation. There were water bodies observed on site that were not identified on any of the plans provided or in the ecological report. | Further assessment | Plan can be provided - requires further coordination with GHD surface water expert and further fieldwork | No - Plan to be provided as Part of Tranche 3.
78. Please provide a plan that shows the location of the Area of Significant Conservation Value in the DCC 2GP and Regionally Significant Wetland by ORC in relation to the site. If there are plans that show the delineated edge of the wetland in relation to the site this would also be useful. | Further assessment | Plan can be provided but is delayed to Tranche 3 | No - Plan to be provided as Part of Tranche 3.

## Air Quality
Green Island Landfill Section 92 Response Landfill Tranche 2
Air quality report
Expert - Peter Stacey
Section 92 request | Desktop, further assessment or fieldwork tranche | Response from technical expert | Information provided
General questions
81. Section 1.2 of the Air Quality Impact Assessment states the scope included review of the instantaneous surface monitoring (ISM) data. Please outline where this is discussed in the Air Quality Assessment. | Desktop | ISM data was included in the annual environmental monitoring reports and was reviewed however was not included because of the methodology used for monitoring. The detection limit of the equipment used was higher than what was required to achieve a reasonable understanding of methane conditions. | Yes - response provided
83. Page 11 of the Air Quality Assessment includes a statement that the document is in draft form. Please confirm that this figure (Figure 2.4) is the final version and can be relied upon. | Desktop | The draft disclaimer is an error, this figure is the final version. The figure will be revised in the updated Air Quality Report to be issued 30 September | No - The figure will be revised in the updated Air Quality Report to be issued 30 September 2023
84.At the site visit, at least two residential properties owned by Dunedin City Council were identified close to the landfill within the landfill designation area. Please include these houses as sensitive receptors in the combustion gas air quality impact assessment | Desktop | Two onsite receptors have been added to the models and rerun. No exceedances were predicted at either receptor. | Yes, partial - Information provided but attachment delayed to updated Air Quality report to be issued 30 September 2023.
92.The emission temperatures for the engine and flare are very high, please justify these selections. | Desktop | Flare exit temperature of 700 ºC was provided to us by the client. Engine exit temperature of 500 ºC was assumed based on our experience with similar equipment. Flare and engine exit temperatures are considered reasonable based on our experience, and available guidance (US EPA. (2003, July). Air Pollution Control Technology Fact Sheet. Flare.). | Yes - response provided
93.Please comment on how the exit velocities for the engine and flare were determined? | Desktop | Exit velocity was assumed to be 10 m/s as a minimum value for this type of discharge based on our experience and discussions with flare equipment suppliers. Flare and engine exit velocities were conservatively selected at the lower end of the range we considered reasonable based on our experience. | Yes - response provided
Landfill gas
101. Please describe how biogas generated at the GIWWTP is combusted and provide biogas combustion rates comparative to the LFG combustion. Has a cumulative assessment of both sources of combustion gas emissions been included in the AQA? | Further assessment | Combustion of biogas from the WWTP was not included in the modelling undertaken for the engine and flare as it is a separate operation to combustion of landfill gas. Emissions from the biogas boilers have not been assessed. The assessed PM10 impacts were required to comply with Regulation 17 of the NESAQ which specifies the maximum incremental offsite impact, therefore a cumulative PM10 assessment was not required. For NO2, SO2 and CO the cumulative impact was assessed based on the default background concentrations given in the MfE’s Good Practice Guide for Assessing Discharges to Air from Industry. The maximum offsite predicted incremental and cumulative impacts made up at most: - 51% and 83% respectively of the NO2 criteria - 15% and 20% respectively of the SO2 criteria - 0.3% and 30% respectively of the CO criteria Emissions from processing of biogas could be up to 6 times more significant than emissions from processing of landfill gas before an exceedance of SO2 would be predicted. CO emissions are even less significant. NO2 emissions are most critical and additional emissions of one third of those from landfill gas processing would predict an offsite exceedance of the criteria. However, due to varying landfill gas and biogas production conditions, source locations and discharge parameters, it is not expected that worst-case 1-hourly average impacts from biogas combustion would occur simultaneously with 1-hourly impacts from landfill gas combustion. In addition, modelled emission rates from processing of landfill gas are worst case based on both the flare and engine operating at full capacity for all hours of the day. Actual processing rates of landfill gas will likely be much less than this. Due to the conservative assumptions made as part of the landfill gas assessment, and the likelihood that worst case emissions and impacts from each source will not occur simultaneously, cumulative impacts from processing of biogas are not expected to be significant, or change the outcomes of the Air Quality Assessment. | Yes - response provided
Odour
102. Complaints by year are graphed in Figure 5.1 of the AQA. Is there any known reason for the complaints in 2018/19 being much higher than in 2020/21? | Desktop | This is delayed to Tranche 3. | No - to be provided in Tranche 3.
103. a) Please provide a full electronic copy of the complaints record that was analysed. b) Where was the complaints data sourced from? c) Please confirm if all complaints that are received by DCC and/or the landfill are forwarded to ORC. | Desktop | The complaints record is provided in the attached folder. Confirmation of b and c to be provided separately if required. | Yes, partial - information provided. See Attachment Q103
104. Please provide a copy of the last three community odour survey reports. | Desktop | The requested information is provided in the attached folder. | Yes - information provided. See Attachment Q104
105. The FIDOL analysis of existing impacts relies on straight-line trajectory for wind directions measured at the site and does not account for meandering wind. This meandering wind is something that was noticed at the site visit and is understood to be common due to the landfill topography. Does the FIDOL assessment and conclusions change if wind meandering is considered? | Desktop | Whilst the meandering plume would lead to some increased frequency of exposure outside of the straight line (between odour source and receptor), it would also act to distribute pollutants across a wider area, potentially decreasing both the severity and duration of odour impacts in the most frequent wind directions. While meandering winds could have some limited impact on the qualitative odour assessment, in our view it will not lead to any changes to the conclusions reached in the assessment or mitigation measures proposed. | Yes - response provided
106. A mitigation objective is stated to be keeping the working face size to a minimum. a) The Design Report recommends no greater than 500m2 “for the majority of the time” – is this achievable and if so, when will it be achieved? If it is not achievable, please explain why and describe how efforts will be made to achieve this recommendation as far as practicable. b) The current operational plan requires a maximum 900m2 working face size (as stated in Section 6.1.1). For context, what was the size of the working face on the day of the site visit (we note that the reason for the current working face size was explained during the site visit, this question relates only to what the actual size was)? c) The proposed consent condition for the working face size is “must not exceed 900m2 , except under some conditions it may be expanded to 1200m2 ”. o This is inconsistent with the Design Report recommendation for 500m2 which is for fire risk mitigation; please propose how the recommendation from the Design Report can be reflected in the consent conditions. o One of the allowed conditions for the expanded working face of 1200m2 is “where landfill gas escape from underneath the day’s refuse, and odour from the day’s refuse are unlikely”. Please explain how this condition would be assessed and interpreted. d) There is a separate recommendation to limit the tip face width to 30m. Please explain why this limitation is needed in addition to the working face area restrictions. | Desktop | Please not the reference to a 500 m2 area in the Design Report is an error and will be addressed in the 30 September update of the report. In regard to the other matters - these will be responded to in the updated LDMP available 30 September. | Yes, partial - also requires update of Design Report and LDMP due to be completed by 30 September 2023
108. “Regular odour scouting” is identified as a proposed mitigation measure for irregular odorous activities. a) Please describe the methodology that will be used for this odour scouting, and whether it will be used regularly or just for irregular loads. Additionally, provide comment on whether the odour scouting can be implemented quickly enough when a load is received? b) Provide confirmation on whether there is any odour scouting carried out now? If so, please provide further information about this including methodology, frequency, and results. | Desktop | a) The odour scouting metholdogy will be developed and included in the updated LMPD which will be provided 30 September. b) No formal odour scouting is currently undertaken. However, Waste Management and DCC are in the process of developing procedures consistent with MfE guidelines and will be documented in the 30 September update of the LMPD. | Yes, partial - further information to be provided in the LDMP 30 September
110. Scheduling to avoid unfavourable meteorological conditions. a) Please comment on the practicality of scheduling activities to avoid unfavourable meteorological conditions, and give at least one example of where and how this has been done at the landfill. b) Please also give examples of where this is likely to be impractical as a mitigation measure. | Desktop | a) For normal landfill operations it is usually practical to schedule odorous activities to favourable conditions. For example disposal of animal carcasses (say Mycoplasma bovis) we would assess the forecast ahead and normally there would be a day in the coming 5-7 that would be best suited for receipt in favourable conditions. That activity would likely require digging a hole in older waste to receive and then immediately cover. Similarly for excavating a trench in recently placed waste for installation of a gas-lateral buried in the waste. This could normally be done in any two-week period with favourable conditions. b) An occasion where it may be “impractical” is during a period of prolonged calm, hot summer weather where the operator received and urgent call for disposal of say rendering plant wastes. It could be that the forecast for the 7-10 days ahead were similar and hence likelihood of unfavourable meteorological conditions. That decision to receive or not and if yes, how to manage would be a difficult decision and require careful weighing of the pros and cons. | Yes - response provided